## Project Timeline
Project Timeline
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Beta Milestones
Date | Milestone | Assigned To | Position | Baseline | Project Timeline Tip
2018-02-08 | Start of Development |  | 5 | 0 | Use the Position field in the Project Milestones table to place the milestone labels where you want! Use positive numbers to position them above the timeline and negative numbers to position them below.
2018-03-01 | Scene Manager | Nathan | -18 | 0
2018-03-01 | Component System | Nathan, Jack | 3 | 0
2018-03-01 | HUD | Nathan | 15 | 0
2018-03-05 | Animation | Elliot | -9 | 0
2018-03-08 | Input Manager | Nathan, Elliot | 12 | 0
2018-03-08 | Physics Solver | Nathan,Ayeesha,Jack | -30 | 0
2018-03-15 | Game Mode and configuration | Nathan | -13 | 0
2018-03-19 | Player mechanics | Jack | 8 | 0
2018-03-19 | Beta Release |  | 5 | 0
2018-03-19 | Basic Items | Nathan, Jack | -5 | 0
2018-05-17 | Submission |  | 5 | 0
0
0
0
0